## Burndown
Story Points
Sprint | Remaining | Done | Added
0 | 62 | 0 | 0
1 | 62 | 0 | 0
2 | 62 | 0 | 0
3 | 54 | 8 | 0
4 | 46 | 8 | 0
5 | 38 | 8 | 0
6 | 32 | 6 | 0
7 | 24 | 8 | 0
8 | 16 | 8 | 0
9 | 8 | 8 | 0
10 | 4 | 4 | 0

## Product Backlog
[7 empty] | Changes | Sprint
Requirement | User Story | Acceptance Tests | Story Points | Created | Author | Contact | date, who, why | Number | Start | End | Status
Golfer Identification | As a golfer, I want the sytem to identify each player so we can compare scores | Each golfer is uniquely identified per the golf session | 6 | 2019-04-21 | us | Golfer-1 | none | 3 | 2019-05-22 | 2019-06-04 | Approved
Num Swing Input | As a golfer, I want to be able to enter number of swings at each hole | Total golf swings for each player is correctly updated after each input | 4 | 2019-04-21 | us | Golfer-1 | none | 3 | 2019-05-22 | 2019-06-04 | Approved
Score Unmodifiable | As a golfer, I don't want my competitor changing the score | Current score is read-only | 4 | 2019-04-21 | us | Golfer-2 | none | 3 | 2019-05-22 | 2019-06-04 | Approved
Ending Score Card | As a golfer, I want to receive a printed score card when the game ends | Print option displays each golfer's score and breakdown by hole | 6 | 2019-04-21 | us | Golfer-2 | none | 4 | 2019-06-05 | 2019-06-18 | Approved
Database Connection | As a Mini-Golf provider, I want a database to keep track of customer scores | Secure persistent storage system with fault tolerance and back-up | 12 | 2019-04-21 | us | Owner | none | 1 | 2019-04-24 | 2019-05-07 | In Progress
User Access Levels | As an employee, I want to be able to add players to the database | Access: Admin- Maintenace; Employee- Create Player & Print Score; Player- update score | 14 | 2019-04-21 | us | Employee-1 | none | 2 | 2019-05-08 | 2019-05-21 | Approved
Coupon on Score Prints | As a Mini-Golf provider, I want coupons printed on scorecards to encourage return visits | Coupon appends to score card prints | 4 | 2019-04-21 | us | Owner | none | 4 | 2019-06-05 | 2019-06-18 | Approved
Formulas:
Start = VLOOKUP([Number],Sprints!$A2:C11,2,FALSE)
End = VLOOKUP([Number],Sprints!$A2:C11,3,FALSE)

## Status
Status
Approved
Deleted
In Progress
Done

## Sprints
Sprint | Start | End
1 | 2019-04-24 | 2019-05-07
2 | 2019-05-08 | 2019-05-21
3 | 2019-05-22 | 2019-06-04
4 | 2019-06-05 | 2019-06-18
5 | 2019-06-19 | 2019-07-02
6 | 2019-07-03 | 2019-07-16
7 | 2019-07-17 | 2019-07-30
8 | 2019-07-31 | 2019-08-13
9 | 2019-08-14 | 2019-08-27
10 | 2019-08-28 | 2019-09-10
Formulas:
Start = [Start, row above] + 14
End = [Start] + 13

## +
Story Points
Sprint | Remaining | Done | Added
0 | 62 | 0 | 0
1 | 62 | 0 | 0
2 | 62 | 0 | 0
3 | 62 | 0 | 0
4 | 62 | 0 | 0
5 | 62 | 0 | 0
6 | 62 | 0 | 0
7 | 62 | 0 | 0
8 | 62 | 0 | 0
9 | 62 | 0 | 0
10 | 62 | 0 | 0